## LUM
Ann & Robert H. Lurie Children's Hospital of Chicago
Closeout Checklist - Local Level Unit Managers
This checklist pertains to all types of sponsored awards and is intended to help guide the user during closeout. It is not an all-inclusive list - some additional tasks may be required.
Fund Number:
PI Name:
Project Title:
Total Project Period:
Task # | Task Description | Completed or N/A? | Specific Actions | Other Information
90 Days Prior to Closeout
1 | Review closeout notification email
2 | Confirm with PI that the technical requirements and subcontracts will be completed as scheduled
3 | If the technical requirements and subcontracts will not be completed as scheduled, submit NCE or new increment request to OSP
4 | Review award expenditures to ensure all expenditures are allowable, allocable, reasonable, and complete, including subawardee expenditures and projects with multiple internal fund numbers and/or PIs
5 | Review committed funds report to identify any pending AP items and ensure timely posting of transactions
6 | Review cost share expenses and verify cost share is fully documented
7 | Submit any necessary corrections to OSPA to ensure they are posted in the GL by the end date
8 | Establish plans for payroll labor template changes and other recurring costs
9 | Notify internal and external service centers about end of project
10 | Check with PI about programmatic deliverables (progress report, patent report, technical report, etc…)
11 | Identify funding sources for anticipated over-expenditures
Immediately Following Award End Date
12 | Ensure all outstanding expenses have posted to the GL
13 | Review determination status of any pieces of equipment
14 | Transfer any over-expenditures off award
15 | Confirm actual cost share matches cost share commitment
16 | Check on status of programmatic deliverables with PI
17 | Identify potential compliance items and follow-up as necessary (traditionally unallowable transactions as identified in UG)
45 Days After End Date
18 | When Lurie Children’s is the recipient of a federal subaward, the PI Closeout Certification Form is due to OSPA 45 days after end date to ensure the final invoicing deadline is met to prime recipient (generally 60 days to submit final invoices to prime federal recipients)
15 Days Before Sponsor Deadline
19 | PI Closeout Certification Form confirming the final figure to be submitted to OSPA
20 | Verify that PI has submitted all programmatic and technical reports to the sponsor or to OSP
21 | If valid award expenses are not yet recorded to GL but in process, the LUM or RBM will provide a reconciliation between the GL balance and final award expenditures (by account category) as they will be reflected in the GL. Supporting documentation for expenses in process must be provided to OSPA as backup documentation.

## RBM
Ann & Robert H. Lurie Children's Hospital of Chicago
Closeout Checklist - Research Business Managers
This checklist pertains to all types of sponsored awards and is intended to help guide the user during closeout. It is not an all-inclusive list - some additional tasks may be required.
Fund Number:
PI Name:
Project Title:
Total Project Period:
Task # | Task Description | Completed or N/A? | Specific Actions | Other Information
90 Days Prior to Closeout
1 | Review closeout notification email
2 | Confirm with PI that the technical requirements and subcontracts will be completed as scheduled
3 | If the technical requirements and subcontracts will not be completed as scheduled, submit NCE or new increment request to OSP
4 | Update Sharepoint record in the 90 Day Report based on correspondence with PI
5 | Review award expenditures to ensure all expenditures are allowable, allocable, reasonable, and complete, including subawardee expenditures and projects with multiple internal fund numbers and/or PIs
6 | Utilizing the fund setup terms and conditions summary page, review non-financial deliverables and reporting schedule and prepare closeout timeline
7 | Review financial obligations in the terms and conditions including, cost sharing, budget line-item restrictions, and financial reporting requirements
8 | Contact other PIs on multi-PI award about variances from budget and any outstanding transactions on their funds
9 | Review committed funds report to identify any pending AP items and ensure timely posting of transactions
10 | Submit any necessary corrections to OSPA to ensure they are posted in the GL by the end date
11 | Establish plans for payroll labor template changes and other recurring costs
12 | Notify internal and external service centers about end of project
13 | Check with PI about programmatic deliverables (progress report, patent report, technical report, etc…)
14 | Reassess award balance and determine if NCE or carry forward request is needed
15 | Identify funding sources for anticipated over-expenditures
Immediately Following Award End Date
16 | Ensure all outstanding expenses have posted to the GL
17 | Review determination status of any pieces of equipment
18 | Transfer any over-expenditures off award
19 | Confirm actual cost share matches cost share commitment
20 | Check on status of programmatic deliverables with PI
21 | Identify potential compliance items and follow-up as necessary (traditionally unallowable transactions as identified in UG)
22 | Verify that all indirect costs have been posted
23 | Verify that all PI salary has been recovered
24 | Notify OSP and OSPA of any extenuating circumstances prohibiting final financial or technical report from being submitted to sponsor or prohibiting final draw down or invoice submission before the sponsor's deadline
45 Days After End Date
25 | When Lurie Children’s is the recipient of a federal subaward, the PI Closeout Certification Form is due to OSPA 45 days after end date to ensure the final invoicing deadline is met to prime recipient (generally 60 days to submit final invoices to prime federal recipients)
15 Days Before Sponsor Deadline
26 | PI Closeout Certification Form confirming the final figure to be submitted to OSPA
27 | Draft financial report to be confirmed with OSPA
28 | Verify that PI has submitted all programmatic and technical reports to the sponsor or to OSP
29 | If valid award expenses are not yet recorded to GL but in process, the LUM or RBM will provide a reconciliation between the GL balance and final award expenditures (by account category) as they will be reflected in the GL. Supporting documentation for expenses in process must be provided to OSPA as backup documentation.

## OSP
Ann & Robert H. Lurie Children's Hospital of Chicago
Closeout Checklist - OSP
This checklist pertains to all types of sponsored awards and is intended to help guide the user during closeout. It is not an all-inclusive list - some additional tasks may be required.
Fund Number:
PI Name:
Project Title:
Total Project Period:
Task # | Task Description | Completed or N/A? | Specific Actions | Other Information
90 Days Prior to Closeout
1 | Prepare closeout notification email, distribute via email to PI, LUM, RBM, and OSPA, and initiate Sharepoint record in the 90 Day Report
2 | Referring back to the original award documentation, confirm RBMs review of non-financial deliverables and closeout timeline
3 | Update reporting due dates for awards with NCE or pending increments
4 | Contact subawardee about variances from budget, outstanding invoices, and request final invoice by specified date
Immediately Following Award End Date
5 | Request a reporting deadline extension request if necessary
15 Days Before Sponsor Deadline
6 | Verify that PI has submitted all programmatic and technical reports to the sponsor or to OSP

## OSPA
Ann & Robert H. Lurie Children's Hospital of Chicago
Closeout Checklist - OSPA
This checklist pertains to all types of sponsored awards and is intended to help guide the user during closeout. It is not an all-inclusive list - some additional tasks may be required.
Fund Number:
PI Name:
Project Title:
Total Project Period:
Task # | Task Description | Completed or N/A? | Specific Actions | Other Information
90 Days Prior to Closeout
1 | Review closeout notification email
2 | Review award expenditures to ensure all expenditures are allowable, allocable, reasonable, and complete, including subawardee expenditures and projects with multiple internal fund numbers and/or PIs
3 | Confirm review of financial obligations and reporting requirements
4 | Update reporting due dates for awards with NCE or pending increments
5 | Review cost share expenses and verify cost share is fully documented
6 | Process journals to ensure transactions and adjustments are completed in the GL by the end date
Immediately Following Award End Date
7 | Ensure all outstanding expenses have posted to the GL
8 | Transfer any over-expenditures off award
9 | Confirm actual cost share matches cost share commitment
10 | Identify potential compliance items and follow-up as necessary (traditionally unallowable transactions as identified in UG)
11 | Verify that all indirect costs have been posted
12 | Verify that all PI salary has been recovered
45 Days After End Date
13 | Submit PI Closeout Certification Form to RBM for PI to confirm the final figure (all charges are allowable, allocable, reasonable, and complete). 45 days is the deadline in which to submit this information, but it is recommended that this is done sooner.
14 | Submit draft final financial report to RBM for review. 45 days is deadline in which to submit this information, but it is recommended that this is done sooner.
10 Days Before Sponsor Deadline
15 | Request final draw, submit final financial report to sponsor, submit final invoice (according to sponsor's procedures)
16 | Apply final draw to respective internal account to ensure that the final income matches the final expenses
17 | In the absence of LUM or RBM confirmation of final award expenditures, OSPA submits final financial reports and requests final letter of credit draws based on general ledger expenditures
18 | PIs, DLOs, LUMs, RBMs, and OSP will be updated on awards that are at risk of meeting this timeline and sponsor deadlines. (Federal agencies de-obligate funds in the letter of credit system after their deadline.)